## Estimation
Phase | Activity | Role | Effort (Hours) | Notes
Requirement Phase | Requirement gathering & clarification with stakeholders | BA / TL | 8 | Assumes requirements already documented in case study
Requirement Phase | NFR elicitation & prioritization | TL | 4 | Cross-platform, performance, SEO, scalability
Design Phase | Solution architecture & technical diagram | Architect / TL | 12 | Includes plugin architecture design
Design Phase | UI/UX wireframes for Home, Search, Showcase, Cart | UX Designer | 16 | 4 key screens
Design Phase | API contract definition with backend team | TL | 8 | Backend out of scope, contract only
Design Phase | Resilience, observability & push notification design | Architect / TL | 8 | Retry/timeout policy, error boundaries, telemetry sink, VAPID/subscription flow
Design Phase | Loading/skeleton & error fallback UX patterns | UX Designer | 6 | Shared across all modules
Design Phase | Backend API design (REST contract, error envelope, data model, security) | Architect / Backend Dev | 12 | Full-stack option
Development Phase | Project scaffolding (Vite + React + TS), CI config | Frontend Dev | 8 | One-time setup
Development Phase | Plugin registry & app shell (routing, header, layout) | Frontend Dev | 12
Development Phase | Home page | Frontend Dev | 12 | Featured products, offers, nav
Development Phase | Product Search module (filters, sort, grid) | Frontend Dev | 24 | Category, price, color, discount, name filters
Development Phase | Product Showcase module | Frontend Dev | 16 | Detail view, size selection, add-to-cart
Development Phase | Shopping cart (add/remove/update/total) | Frontend Dev | 16 | Business logic + drawer UI
Development Phase | Payment gateway integration (UI + stub/real) | Frontend Dev | 16 | Assumes gateway SDK provided
Development Phase | Pluggable offers/banner widget | Frontend Dev | 12 | Configurable show/hide, theme
Development Phase | Cross-browser & responsive fixes | Frontend Dev | 16 | Chrome, Edge, Firefox, Safari, mobile
Development Phase | SEO baseline (meta tags, semantic HTML, pre-render eval) | Frontend Dev | 8
Development Phase | Mock API server for parallel development | Frontend Dev | 8 | Node/Express + static JSON
Development Phase | PWA: manifest, service worker caching, update prompt | Frontend Dev | 12 | NFR: fast repeat load, offline start-up
Development Phase | Web Push notifications (SW handlers, subscription client, header toggle, mock push endpoints) | Frontend Dev | 16 | NFR: re-engagement; HTTPS + VAPID keys
Development Phase | Resilient HTTP client, module error boundaries, telemetry hook | Frontend Dev | 12 | NFR: resilience, observability
Development Phase | Skeleton loaders, image and error fallback UI | Frontend Dev | 12 | NFR: smooth UI / 100ms perceived budget
Development Phase | Module feature flags (env-driven) | Frontend Dev | 4 | VITE_DISABLED_MODULES
Development Phase | CI pipeline (lint, test, build) | Frontend Dev / DevOps | 6 | GitHub Actions
Development Phase | Storybook setup and component/module stories | Frontend Dev | 16 | Living UI documentation with mocked data
Development Phase | Monorepo setup (npm workspaces, Turborepo, shared contract package) | Frontend Dev / DevOps | 8 | Single install, cached builds, one CI entry point
Development Phase | Backend API: catalog search, product, categories/colors endpoints | Backend Dev | 16 | Express + TypeScript + zod validation
Development Phase | Backend API: server-side pricing/quote and orders | Backend Dev | 16 | Never trusts client prices; stock checks
Development Phase | Backend API: Web Push subscription and broadcast | Backend Dev | 8 | VAPID, admin-key protected broadcast
Development Phase | Backend: PostgreSQL persistence, migrations, idempotent orders, TLS options | Backend Dev | 16 | Idempotency-Key header; JSON fallback without DATABASE_URL
Development Phase | Structured logging (pino) with masking, telemetry and analytics endpoint | Backend Dev | 8 | NFR: observability
Development Phase | SCSS design tokens and shared ui/ components | Frontend Dev | 12 | Button, Card, Field, Heading, Table
Development Phase | Rule-based Chatbot assistant | Frontend Dev | 8 | responses.json intents; localStorage history
Development Phase | Dockerfiles and docker-compose (postgres, api, web) | DevOps | 8 | Multi-stage, non-root images
Development Phase | Backend hardening: helmet, CORS allow-list, rate limiting, error envelope, config | Backend Dev | 8 | OWASP baseline
Development Phase | PostgreSQL persistence: schema migrations, seeding, repositories, docker-compose | Backend Dev | 16 | Products, orders, push subscriptions; parameterized queries
Development Phase | Cart persistence, URL-synced search filters, debounced search, request cache | Frontend Dev | 12 | localStorage with validation; useSearchParams mirror; TTL cache with in-flight de-dup
Development Phase | Checkout flow: order placement from the cart drawer | Frontend Dev | 8 | orderService (non-retried POST), confirmation and error states
Development Phase | Accessibility hardening: focus-managed cart dialog, live regions, WCAG AA contrast | Frontend Dev | 8 | axe checks in Playwright
Development Phase | Telemetry/analytics events stored locally via API JSON file; global error capture; log masking; CSP/security headers | Frontend Dev | 6 | VITE_TELEMETRY_URL (optional), public/_headers
Development Phase | Repo quality gates: Husky, lint-staged, commitlint, bundle budget, Dependabot, npm audit | Frontend Dev / DevOps | 6 | Conventional Commits, pre-commit checks, CI budget
Testing & Bug Fixing Phase | Unit tests for business layer (cart, filters) | Frontend Dev | 12 | Vitest
Testing & Bug Fixing Phase | Component, service and module tests (Testing Library) | Frontend Dev | 24 | ~110 tests covering loading/error/retry states, persistence, checkout and focus handling
Testing & Bug Fixing Phase | Backend API tests (supertest) incl. validation, security and pricing | Backend Dev | 16 | ~40 tests
Testing & Bug Fixing Phase | Playwright end-to-end tests (desktop + mobile, incl. axe accessibility) | QA / Frontend Dev | 16 | ~21 scenarios x 2 projects
Testing & Bug Fixing Phase | Push, offline and PWA install testing on real devices | QA | 8 | Android/Chrome, desktop Edge/Chrome, iOS Safari (installed PWA)
Testing & Bug Fixing Phase | Manual functional & cross-browser testing | QA | 16
Testing & Bug Fixing Phase | Bug triage & fixes | Frontend Dev / QA | 16
Testing & Bug Fixing Phase | Performance validation (load time, interaction latency) | QA / Frontend Dev | 8 | 100ms interaction budget
Project Management | Planning, status reporting, reviews | TL / PM | 16 | Across full 4-week duration
Project Management | Risk management & stakeholder communication | TL / PM | 8
Phase Totals
Requirement Phase |  |  | 12
Design Phase |  |  | 62
Development Phase |  |  | 390
Testing & Bug Fixing Phase |  |  | 116
Project Management |  |  | 24
Grand Total |  |  | 604 | ≈ 76 person-days (16 person-weeks)

## Assumptions & Scope
Category | Item
In Scope | Home, Product Search, Product Showcase, Shopping Cart, Payment Gateway UI (frontend only)
In Scope | Plugin-based architecture with at least one fully working functional module
In Scope | Full-stack option: Express/TypeScript backend (catalog, pricing, orders, push) in a Turborepo monorepo with shared types
In Scope | Mock backend APIs for development/demo purposes
In Scope | PWA (offline app shell), Web Push opt-in, resilient HTTP client, error boundaries, telemetry hook, feature flags, CI, Storybook
Out of Scope | Production push campaign tooling, audience segmentation and VAPID key management
Out of Scope | Production hosting, managed Postgres provisioning/backups and payment processor (local docker-compose Postgres provided)
Out of Scope | Real payment processor integration and PCI compliance work
Out of Scope | Admin/inventory management back-office screens
Assumption | Client provides production REST APIs matching the documented contract
Assumption | Moderate catalog size; pagination/server-side search can be added later without redesign
Assumption | Only evergreen browser support required (no IE11)
Assumption | Application is served over HTTPS (required for service workers and Web Push)
Assumption | Production telemetry/analytics collector (Sentry/App Insights) is provided by client; the sample stores events in a local JSON file via the API